## Gantt Chart
ISEC3004-Assignment 01- Group13
Assignment NAME: | CSRF and Log Injection ( Group Assignemnt)
MODULE / GROUP: | Group Members: Sadinya, Kristina, Bhagya, Ameli, Arindi
DATE STARTED: | 2026-09-18
DATE ENDED: | 2026-10-07
# | TASK | ASSIGNEE | LABEL | DATE STARTED | DATE ENDED | DAYS | PROGRESS | September 2026 | [12 empty] | October 2026
[8 empty] | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07
Phase 1: Setup & Research (Sept 18-20)
1 | Setup GitHub repo, Projects board & branches | Sadinya | management | 2026-09-18 | 2026-09-18 | 1 | 100% | bar: 2026-09-18
2 | Create Gantt chart / milestone schedule | Sadinya | management | 2026-09-18 | 2026-09-19 | 2 | 100% | bar: 2026-09-18 to 2026-09-19
3 | Record Meeting Minutes (Planning) | Sadinya | management | 2026-09-18 | 2026-09-18 | 1 | 100% | bar: 2026-09-18
4 | Research CSRF vulnerability (OWASP, theory) | Kristina | research, csrf | 2026-09-18 | 2026-09-20 | 3 | 100% | bar: 2026-09-18 to 2026-09-20
5 | Research Log Injection vulnerability (OWASP, theory) | Bhagya | research, log-injection | 2026-09-18 | 2026-09-20 | 3 | 100% | bar: 2026-09-18 to 2026-09-20
6 | Install & test Burp Suite setup | Ameli | research, csrf | 2026-09-19 | 2026-09-20 | 2 | 100% | bar: 2026-09-19 to 2026-09-20
7 | Test logging tools & log file analysis | Arindi | research, log-injection | 2026-09-19 | 2026-09-20 | 2 | 100% | bar: 2026-09-19 to 2026-09-20
Phase 2: Vulnerable Code Development (Sept 21-23)
8 | Write CSRF vulnerable code (profile update without token) | Kristina | coding, vulnerable, csrf | 2026-09-21 | 2026-09-22 | 2 | 100% | bar: 2026-09-21 to 2026-09-22
9 | Create CSRF exploit payload (malicious HTML form) | Kristina | exploit, csrf | 2026-09-22 | 2026-09-23 | 2 | 100% | bar: 2026-09-22 to 2026-09-23
10 | Write vulnerable logging code (direct user input concatenation) | Bhagya | coding, vulnerable, log-injection | 2026-09-21 | 2026-09-22 | 2 | 100% | bar: 2026-09-21 to 2026-09-22
11 | Create Log Injection CRLF payload (\r\n injection) | Bhagya | exploit, log-injection | 2026-09-22 | 2026-09-23 | 2 | 100% | bar: 2026-09-22 to 2026-09-23
12 | Integrate both vulnerabilities into single Flask app | Sadinya | integration, coding | 2026-09-23 | 2026-09-23 | 1 | 100% | bar: 2026-09-23
13 | Write README.md with setup instructions | Sadinya | integration, management | 2026-09-23 | 2026-09-23 | 1 | 100% | bar: 2026-09-23
Phase 3: Exploit & Tracing (Sept 24-26)
14 | Capture CSRF traces using Burp Suite (screenshots) | Ameli | tracing, csrf | 2026-09-24 | 2026-09-25 | 2 | 100% | bar: 2026-09-24 to 2026-09-25
15 | Capture Log Injection traces from app.log (screenshots) | Arindi | tracing, log-injection | 2026-09-24 | 2026-09-25 | 2 | 100% | bar: 2026-09-24 to 2026-09-25
16 | Interpret CSRF evidence & link to vulnerability | Ameli | tracing, report, csrf | 2026-09-25 | 2026-09-26 | 2 | 100% | bar: 2026-09-25 to 2026-09-26
17 | Interpret Log Injection evidence & link to vulnerability | Arindi | tracing, report, log-injection | 2026-09-25 | 2026-09-26 | 2 | 100% | bar: 2026-09-25 to 2026-09-26
18 | Record Meeting Minutes (Exploit Review) | Sadinya | management | 2026-09-26 | 2026-09-26 | 1 | 100% | bar: 2026-09-26
Phase 4: Mitigation & Verification (Sept 27-30)
19 | Implement CSRF mitigation (Synchronizer Token Pattern) | Ameli | mitigation, csrf | 2026-09-27 | 2026-09-28 | 2 | 100% | bar: 2026-09-27 to 2026-09-28
20 | Implement Log Injection mitigation (input sanitization) | Arindi | mitigation, log-injection | 2026-09-27 | 2026-09-28 | 2 | 100% | bar: 2026-09-27 to 2026-09-28
21 | Test CSRF mitigation - verify attack fails (403 Forbidden) | Ameli | testing, qa, csrf | 2026-09-28 | 2026-09-29 | 2 | 100% | bar: 2026-09-28 to 2026-09-29
22 | Test Log Injection mitigation - verify sanitized logs | Arindi | testing, qa, log-injection | 2026-09-28 | 2026-09-29 | 2 | 100% | bar: 2026-09-28 to 2026-09-29
23 | Create QA Testing Checklist for CSRF | Ameli | qa, csrf | 2026-09-29 | 2026-09-30 | 2 | 100% | bar: 2026-09-29 to 2026-09-30
24 | Create QA Testing Checklist for Log Injection | Arindi | qa, log-injection | 2026-09-29 | 2026-09-30 | 2 | 100% | bar: 2026-09-29 to 2026-09-30
25 | Merge all mitigation branches into main | Sadinya | integration, qa | 2026-09-30 | 2026-09-30 | 1 | 100% | bar: 2026-09-30
Phase 5: Report Writing (Oct 1-4)
26 | Write Report: CSRF Overview + Vulnerable Code + Exploit | Kristina | report, csrf | 2026-10-01 | 2026-10-02 | 2 | 100% | bar: 2026-10-01 to 2026-10-02
27 | Write Report: CSRF Detection, Tracing, Mitigation, Verification | Ameli | report, csrf | 2026-10-01 | 2026-10-02 | 2 | 100% | bar: 2026-10-01 to 2026-10-02
28 | Write Report: Log Injection Overview + Vulnerable Code + Exploit | Bhagya | report, log-injection | 2026-10-01 | 2026-10-02 | 2 | 100% | bar: 2026-10-01 to 2026-10-02
29 | Write Report: Log Injection Detection, Tracing, Mitigation, Verification | Arindi | report, log-injection | 2026-10-01 | 2026-10-02 | 2 | 100% | bar: 2026-10-01 to 2026-10-02
30 | Write Report: Introduction + Team Organisation + Conclusion | Sadinya | report, management | 2026-10-02 | 2026-10-03 | 2 | 100% | bar: 2026-10-02 to 2026-10-03
31 | Write Report: Project Management Evidence (screenshots) | Sadinya | report, management | 2026-10-02 | 2026-10-03 | 2 | 100% | bar: 2026-10-02 to 2026-10-03
32 | Format & proofread final report | Sadinya | report, qa | 2026-10-03 | 2026-10-04 | 2 | 100% | bar: 2026-10-03 to 2026-10-04
33 | Record Meeting Minutes (Report Review) | Sadinya | management | 2026-10-04 | 2026-10-04 | 1 | 100% | bar: 2026-10-04
Phase 6: Presentation & Submission (Oct 5-7)
34 | Create presentation slides (CSRF section) | Kristina & Ameli | presentation, csrf | 2026-10-05 | 2026-10-05 | 1 | 100% | bar: 2026-10-05
35 | Create presentation slides (Log Injection section) | Bhagya & Arindi | presentation, log-injection | 2026-10-05 | 2026-10-05 | 1 | 100% | bar: 2026-10-05
36 | Create PM & QA evidence slides | Sadinya | presentation, management | 2026-10-05 | 2026-10-06 | 2 | 100% | bar: 2026-10-05 to 2026-10-06
37 | Rehearse live demonstration (all 5 members) | All | presentation, demo | 2026-10-06 | 2026-10-06 | 1 | 100% | bar: 2026-10-06
38 | Final submission - Report + Code ZIP | Sadinya | management | 2026-10-07 | 2026-10-07 | 1 | 100% | bar: 2026-10-07
| OVERALL PROJECT PROGRESS |  |  | 2026-09-18 | 2026-10-07 | 20 | 100%
Note on E57: Assumption: year 2026 used for all dates; phase date windows taken from the uploaded task list.

## Milestones & Labels
MILESTONES
Milestone | Start Date | Due Date | Status
Phase 1: Setup & Research | 2026-09-18 | 2026-09-20 | Due passed
Phase 2: Vulnerable Code Development | 2026-09-21 | 2026-09-23 | Due passed
Phase 3: Exploit & Tracing | 2026-09-24 | 2026-09-26 | Due passed
Phase 4: Mitigation & Verification | 2026-09-27 | 2026-09-30 | Due passed
Phase 5: Report Writing | 2026-10-01 | 2026-10-04 | Due passed
Phase 6: Presentation & Submission | 2026-10-05 | 2026-10-07 | Due passed
GITHUB LABELS
Label | Purpose
research | Research tasks
coding | Development work
vulnerable | Vulnerable code
exploit | Exploit development
tracing | Detection / tracing
mitigation | Security fixes
testing | QA / testing
qa | Quality assurance
integration | System integration
report | Report writing
presentation | Presentation prep
management | PM tasks
csrf | CSRF related
log-injection | Log injection related
demo | Live demo
Formulas:
Status = IF(TODAY()>[Due Date],"Due passed",IF(TODAY()>=[Start Date],"In progress","Not started"))